{"text_format":"1","workbook":"xlsx","n_sheets":2,"sheets":["Sheet1","Changes"],"not_rendered":{"charts":0,"images":18,"macros":1,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":88,"n_cols":6,"rows_kept":88,"cut":false,"hidden":false,"merged":[[81,0,81,1],[83,0,83,1],[85,0,85,1],[71,0,71,1],[72,0,72,1],[73,0,73,1],[75,0,75,1],[77,0,77,1],[64,0,64,4],[65,0,65,1],[67,0,67,1],[69,0,69,1],[79,0,79,1],[4,0,4,1],[24,0,24,1],[23,0,23,1],[41,0,41,4],[42,0,42,1],[36,0,36,1],[34,0,34,1],[35,0,35,1],[25,0,25,1],[26,0,26,1],[27,0,27,1],[29,0,29,1],[30,0,30,1],[23,2,35,4],[2,5,2,6],[15,0,15,1],[0,0,0,4],[21,0,21,4],[37,0,39,4],[1,0,1,4],[17,0,17,1],[19,0,19,1],[28,0,28,1],[3,0,3,1],[6,0,6,1],[8,0,8,1],[10,0,10,1],[12,0,12,1],[14,0,14,1],[2,0,2,1],[21,5,21,6],[31,0,31,1],[32,0,32,1],[33,0,33,1],[87,0,89,4],[44,0,44,1],[46,0,46,1],[48,0,48,1],[49,0,49,1],[50,0,50,1],[52,0,52,1],[54,0,54,1],[56,0,56,1],[58,0,58,1],[60,0,60,1],[62,0,62,1]]}
["PLEASE CHECK THIS SCHEDULE OFTEN\n AS IT IS SUBJECT TO CHANGE"]
["SUMMER 2021 OVERLAY PROJECT SCHEDULE"]
["Location",null,"Durration","Start Date","Completion Date","Location Map (click black button to view map)"]
["Kimball Junction",null,"34 days","2021-06-10","2021-07-28"]
["  Night paving",null,"5 days","2021-06-21","2021-06-25"]
[]
["Old Ranch rd",null,"24 days","2021-06-15","2021-08-02"]
[]
["Hoytsville Road",null,"24 days","2021-06-28","2021-07-28"]
[]
["Service Area 3",null,"18 days","2021-07-19","2021-08-12"]
[]
["Snyder's Mill",null,null,"2021-06-14","Dependent on concrete availability"]
[]
["Mahogany Hills",null,"47 days","2021-06-23","2021-08-31"]
["Majority Overlay",null,"9 days","2021-08-12","2021-08-24"]
[]
["Bear Hollow Drive",null,"10 days","2021-08-16","2021-08-27"]
[]
["Trail Interconnect",null,"18 days","2021-08-23","2021-09-15"]
[]
["SUMMER 2021 SLURRY SEAL PROJECT SCHEDULE",null,null,null,null,"Location Map (click black button to view map)"]
[]
["Highland Estates",null,"Slurry Projects will be completed between July 1 and July 14.\n\n(exact dates for each location coming soon)"]
[]
["Kimball Junction"]
[]
["Silver Springs"]
[]
["Pine Brook"]
[]
["Canyons"]
[]
["Public Works"]
[]
["Kamas Parking lots"]
[]
["Please direct questions and concerns to Spencer Nielson at:\nsnielson@summitcounty.org \n(453) 336-3291"]
[]
[]
[]
["PUBLIC WORKS CHIP SEAL 2021 SCHEDULE"]
["Location",null,"Durration","Start Date","Completion Date"]
[]
["Echo Canyon",null,"1 days","2021-07-12","2021-07-12"]
[]
["Yellow Creek",null,"1 days","2021-07-13","2021-07-13"]
[]
["Chalk Creek",null,"4 days","2021-07-14","2021-07-15"]
[]
["Lambert Lane",null,"1 days","2021-07-27","2021-07-27"]
[]
["Hallam Dr",null,"1 days","2021-07-27","2021-07-27"]
[]
["Woodland Hills",null,"1 days","2021-07-28","2021-07-28"]
[]
["West Hoytville",null,"1 days","2021-07-29","2021-07-29"]
[]
["Division Street",null,"1 days","2021-07-29","2021-07-29"]
[]
["Kilby Rd",null,"1 days","2021-08-02","2021-08-02"]
[]
["Silver Creek ",null,"2 days","2021-08-03","2021-08-04"]
[]
["PUBLIC WORKS FOG SEAL 2021 SCHEDULE"]
["Location",null,"Durration","Start Date","Completion Date"]
[]
["Echo Canyon",null,"1 days","2021-07-19","2021-07-19"]
[]
["Yellow Creek",null,"1 days","2021-07-20","2021-07-20"]
[]
["Chalk Creek",null,"2 days","2021-07-21","2021-08-06"]
[]
["Lambert Lane",null,"1 days","2021-08-05","2021-08-05"]
[]
["Hallam Dr",null,"1 days","2021-08-05","2021-08-05"]
[]
["Woodland Hills",null,"1 days","2021-08-05","2021-08-05"]
[]
["West Hoytville",null,"1 days","2021-08-09","2021-08-09"]
[]
["Division Street",null,"1 days","2021-08-09","2021-08-09"]
[]
["Kilby Rd",null,"1 days","2021-08-09","2021-08-09"]
[]
["Silver Creek ",null,"2 days","2021-08-10","2021-08-10"]
[]
["Please direct questions and concerns to Spencer Nielson at:\nsnielson@summitcounty.org \n(453) 336-3291"]

{"sheet":"Changes","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}